## RUNNING-NEW PROJECT LIST
PROJECT LIST
S. No. | Folder No. | AK Job No. |  |  |  |  | Project Details |  |  | Tender NET Area | PT SLAB DETAILS |  | PT Slabs Concreted Details |  |  | Balance Concreting PT Slab Details |  |  | TOTAL ACTUAL PROJECT AREA | SITE STATUS (09-05-26) | [13 empty] | CLOSEOUT DOCUMENTS |  |  | COMMERCIAL STATUS | [6 empty] | PROJECT TRACKING
[20 empty] | MATERIAL |  | INSTALLATION |  |  | CONCRETE Done/ In Progress/ Scheduled | STRESSING |  |  | GROUTING |  |  | AREA/INVOICE VERIFICATION |  |  |  |  | INVOICE & PAYMENT CERTIFICATE |  |  | PAYMENT DETAILS |  | OVERDUE DETAILS (For Followup)
|  |  | PM/ Sr. P.E. | Engineer | Supervisor/ Technician/ Labor | Nos. | Project Name | Plot No | Location |  | Description | Nos. | Slabs | Nos. | Area | Slabs | Nos. | Area |  | PO Issued floor/ Status - Hold | Material Available at site for floors | Strand Cutting & Marking | Laying/ Installation | Maintenance/ Top steel Progress |  | Stressing Preparation/ To Start | Stressing in Progress/ Expected Finish | Stressing Report Done/ Balance | Grouting in Progress | Grouting Completed | Grouting Pending for Concreted Slabs | To do | Status | As Built Drawing Last completed level | As Built Drawing Balance to do | Submission Status | Claimed Slabs till date | Payment Certificate Received Slabs till date | Pending Payment Certificates for slabs | Payment received for slabs | Received Amount till date (includes PDC recd) | Overdue Amount for Slabs | Overdue Payment amount | Project status | Running Count | Expected Completion DATE | Expected START DATE
1 | 109 | AK-23-037 | Ravi | Sattish | Venkateshwar | 1 | Iraz Properties Globecon Contracting | 326-0870 | Al Jadaf | 15559 | B1, GF, 1 to 13, Lroof | 16 | B1, GF, 1, 2, 3,4 | 6 | 6882 | 5 to 13, Lroof | 10 | 8677 | 15559 |  |  |  |  | 5 |  |  |  | 4 bal |  | B1, GF, 1,2 | LEVEL-3, 4 |  |  | Nil | B1, GF, 1st |  | upto 2 on 24/01 | To update | To update | Upto Level 1 | Nil | Nil | NIl | Running | 1 | 2026-09-01
2 | 121 | AK-23-256 | Sadayappan | Dharmendran | Dinesh Kumar | 1 | JULFAR CONTRACTING PLOT 002 | JVC13LHRS002 | JVC, Dubai | 24263 | P1,P2,P3, 1 to 23, Roof | 27 | P1, P2, P3,1 to 22 | 25 | 22747 | 23, Roof | 2 | 1516 | 24263 |  |  |  | 23 |  |  |  |  | 22 done |  | upto 20 | 21,22 |  |  | To Do | Upto 14 |  | upto 16 on 24/01 | To update | To update | To update | To update | To update | To update | Running | 1 | 2026-06-01
3 | 151 | AK-23-278 | Sadayappan | Raman/ Sadayappan | RAMAN ALAGAPPAN, Durai Palani, Chinnadurai Periyasamy, Venkatesh Shaktivel, Vigneshwaran, | 5 | Abdul Azizi | 2320300 | Al Qusais, Dubai | 87079 | 1 to 13, LR, UR | 15 | 1 to 8, lvl 9 pt3, 4, 5 & lvl 10 pt 4, 5 & 11th pt 4 | 8 | 53047.82 | 9th pt-1, 10th pt 1,3 -11th pt1,3,5 & 12, 13, R | 8 | 34031 | 87078.82 |  |  |  | Lvl 10 Part 3 | 9th part 2 |  | 9th part 2 & 11th part 4 |  |  |  | Lvl 2, 3, 4, 5 all Done | lvl 6, 7, 8, lvl 9- pt3,4,5 |  |  | NIL | All Floors Balance | - | upto lvl 7 on 24/01/26 | Nil |  | Upto 4th Pt 5 | 5 | Level 5 | 140738 | Running | 1 | 2026-10-01 | N/A
4 | 162 | AK-23-136 | Ravi | Moustafa | SIVAKUMAR PERUMAL + TAHA | 2 | Tiger_Renald tower_2B+G&M+4P+37F+R | C10A | Reem Island, Abu Dhabi | 40909 | B1,GF,M, P1-P4, L1, Deck L1, L2-L13, L15-L37, RF | 43 | B1, GF, M, P1, P2, P3,P4, 1 - 13, 15-20-22 | 28 | 28746.99 | L23-L37, RF | 15 | 12162.4 | 40909.39 |  |  | 29 | 28 RCC SLAB |  |  |  |  | 27 done | 25 | upto 24 | 26,27, 28RCC slab | Upto 13 | Done | Nil | Upto 13 | NS | upto 15th on 24/01 | To update | To Update | To Update | To Update | To Update | To Update | Running | 1 | 2026-10-01
5 | 175 | Ak-24-257 | Ravi | Moustafa | Manikandan Ayyasamy | 1 | Tiger_ Volga Tower | JVT07JNEW001 | JVT, Dubai | 89718 | P1-P4, 1-40, R | 45 | P1 to P4, 1 to 16-18 pa1 | 21 | 46277.08 | 18 pa2 to 40 + R | 24 | 31607.64 | 77884.72 |  |  |  | 25 P2 | 25 P1 |  |  | 24 P2 | 24 P1 done | 22 | Gtg lvl 21 done | 23 |  |  | Nil | Upto 13 | NS | upto 13th on 24/01 | To update | To Update | To Update | To Update | To Update | To Update | Running | 1 | 2026-12-01
6 | 178 | AK-24-23 | Sadayappan | Dharmendran |  |  | Bin Malek contracting | 6439821 | Wadi Al Safa 2, Dubai | 3539 | 1,2,3,4,5, Roof | 6 | 1,2,3, 4, 5 | 5 | 2969 | Roof | 1 | 570 | 3539 |  |  |  |  | on hold | [6 empty] | 4, 5 bal |  |  | Nil | All Balance |  | To update | To update | To update | To update | To update | To update | To update | Running | 1
7 | 190 | AK-24-110 | Ravi | Moustafa | Eslam Soliman + Medhat | 2 | Samana Ivy Garden- Modern Contracting | 6488665 | Dubai Land Residence Complex | 44862 | B1, GF, 3P, 1, 2-14, R | 20 | B1, GF, P1, P2, P3, 1, 2, 3PA1 | 7 | 23389.58 | 3PA2-14, R | 13 | 27404.2 | 50793.78 |  |  | lvl 6 | [7 empty] | GF, P1, P2, P3, 1 to 3 Done | 4, 5 |  |  | Nil | GF, P1 to P3 | NS | Pod 3 | Pod 1 | Pod 2, 3 | Pod 1, 2 | Pod 3 | Pod 3 | 63739 | Running | 1 | 2026-10-01
8 | 219 | AK-24-140 (Makany) Bldg 6 | Ravi | Sattish | Selvamani Annamalai, MOHAMMAD ASHRAF(Hassan) ALI | 2 | Pivot Abu Dhabi | Town Plaza, Reem Hills | Phase 2, Abu Dhabi | 181191.1 | podium-1 to pdoium-2, level-1 to level13, roof | 16 | podium-1-podium-2, level-1 to level-9 part-1 | 10 | 82540 | level-9 part-2, leve-10-level-13, roof | 6 | 20899 | 103439 |  |  |  |  | lvl 8 pt 2 |  |  | lvl 8 Pt1 | lvl 6 Pt 1 Rep Bal |  | upto lvl 9 | lvl 10 pt1 | Bldg 5, 6 upto lvl 10 completed |  | To Do | All Balance |  | To update | To update | To update | To update | To update | To update | To update | Running | 1 | 2026-04-01
|  | AK-24-140 (Maskan) Bldg 5 | Ravi | Sattish | SENTHIL KUMAR, DINESH MARUDAI, Sanyasi Mani; Lamloum Ibrahim | 4 |  |  |  |  | podium-1 to pdoium-2, level-1 to level13, roof | 16 | podium-1-podium-2, level-1 to level-8 | 10 |  | level-9-level-13, roof | 6 |  | 0 |  |  |  | Lvl 8 |  |  |  |  | Lvl 7 done |  | upto lvl 8 done; | lvl 9 bal; lvl 10 pt 2 |  |  | To Do | All Balance |  | To update | To update | To update | To update | To update | To update | To update
|  | AK-24-140 (Majlis) Bldg 3 |  | Sattish | Mohamed Badr, Sr Badr, Chinnasamy Massy | 3 |  |  |  |  | podium-1 to pdoium-2, level-1 to level13, roof | 16 | podium-1 to pdoium-2, level-1 to level13, roof | 16 | 92417 | - | - | 0 | 92417 | [10 empty] | upto lvl 6, Lvl7pt1; lvl 8 | level7 pt2;-level 9-13, roof |  |  | To Do | All Balance |  | To update | To update | To update | To update | To update | To update | To update
|  | AK-24-140 (Manzel) Bldg 4 |  | Sattish | SURESH KANDAN, ESLAM Emadeldin | 2 |  |  |  |  | podium-1 to pdoium-2, level-1 to level13, roof | 16 | podium-1 to pdoium-2, level-1 to level13, roof | 16 |  | - | - |  | 0 | [10 empty] | upyo 8 all Gtg done; | level-9-to 13, roof, non tower area |  |  | To Do | All Balance |  | To update | To update | To update | To update | To update | To update | To update | Running | 1
9 | 220 | AK-24-572 |  |  |  |  | Model Consltant (B+G+5P+38+R) | JVC10AHRG001C | JVC, Dubai | 43818 | P1-P5, 1-38, R | 44 | 0 | 0 | 0 |  | 44 |  | 0 | [24 empty] | Contractor TBA
10 | 229 | AK-24-592 (186) | Ravi | Sattish |  | 0 | INDO GULF CONTRACTING +Emsquare | 6253206 (P186) | Wadi Al Safa 3, Dubai | 11154 | GF, 1-5, R, TR | 8 | GF, 1 | 2 | 3393.03 | 2-5, R, TR | 6 | 5909.97 | 9303 | [10 empty] | GF, 1, |  |  |  | Nil | GF, 1 |  | GF, 1 | To Update | To Update | GF | 1 | 1 | To update | On Hold
11 | 230 | AK-24-609 |  |  |  |  | Model- Wog Capital, G+P+6+R | 1010529 | Nakhlat Deira, Dubai | 10302 | P, 1-6, Lroof | 8 | [6 empty] | 0 | [24 empty] | Contractor TBA
12 | 236 | AK-24-482 |  |  |  |  | Model Engg, G+2P+8+R | 3340679 | Jumeirah Garden City, Dubai | 24290 | P1, P2, 1-8, R | 11 | [6 empty] | 0 | [24 empty] | Contractor TBA
13 | 237 | AK-24-447 | Ravi | Sattish | Palani Muthu | 1 | NSE contracting [Same as ak-23-376] G+3p+17+R | 6817436 | Jumeirah Village, Dubai | 36726 | P1-P4, 1-17, LRDECK | 22 | Podium-1 TO Podium-4, Level-1-Level-11 | 15 | 31151 | Level-12-Level-17,LR Deck slab | 7 | 5575 | 36726 |  |  |  |  | 12 |  | 11 ZB | 11 zA |  |  | upto lvl 7 done | lvl 3, 4 bal |  |  | Nil | Upto lvl 7 |  | upt 8 Zb, 6th Za on 24/01 | To Update | To Update | To Update | To Update | To Update | To Update | Running | 1 | 2026-06-01
14 | 238 | AK-23-383 | Sadayappan | Sadayappan | Muthu Mayakannan, | 1 | Al Tawoos Contr. G+P+6+R | 5919556 | Wasl Gate, Jabal Ali 1st, Dubai | 14661 | P1, 1-6, R, TR | 9 | P1, 1,2,3 | 4 | 8135 | 4-6, R, TR | 5 | 6526 | 14661 | [10 empty] | Podium, 1st, 2nd, 3rd pt 1 | 3 pt2,3 | [5 empty] | 1st on 24/12 | To Update | To Update | 1st | Nil | Nil | 0 | Running | 1 | 2026-06-01
15 | 243 | AK-25-049 | Ravi | Moustafa | Ali Mahrous | 1 | Al Rabat Cont. 1B+G+1P+13+R | 6488733 | Wadi Al Safa 3, Dubai | 19533 | G, 1-13, Roof | 15 | G, 1, 2, 3, 4, 5, 6.7 | 8 | 12631 | 8-13, R | 7 | 9636 | 22267 | [8 empty] | lvl 9 done |  | GF Gtg Done; P1, 1 - 7 done | 8. 9 |  |  | Nil |  |  | upto 4 on 24/01 | To update | To Update | To Update | To Update | To Update | To Update | Running | 1 | 2026-07-01
16 | 247 | AK-24-661 |  |  |  |  | Model Consultant_P-772 -2B+G+11+M+R - Sky Island | 6488721 | Wadi Al Safa 5, Dubai | 10494 | 1 TO 11, LR, UR | 13 |  | 0 |  |  | 13 |  | 0 | [24 empty] | TO START
17 | 249 | AK-24-526 | Sadayappan | Dharmendran | Arun Kumar | 1 | Al Shafar G+1 Comm | 3321846 | Jumeirah 1, Dubai | 4128 | 1, Roof | 2 | 1, ROOF | 2 | 3000 | 1ST PT 4, ROOF PT 4 | 0.5 | 1128 | 4128 | [8 empty] | 1 Pt1,2, 3 Rep Done |  |  | 1 Pt1,2, 3 |  |  | To Do |  |  | 1st Pt 1,2,3 on 24/01 | Nil | To update | To update | To update | To update | To update | Running | 1 | 2026-01-01
18 | 250 | AK-25-070 | Ravi | Sattish | Manikandan Marimuttu | 1 | DSCA Luminar 1 - (152475) | Luminar 1 - (152475) PLOT NO. JVT02HHRA002B | JVT, Dubai | 25334 | P1 tp P5, P5 High lvl, 1-20, Roof | 26 | Podium-1 to Podium-5 , Podium-5 High level, Level-1 to Level-7 | 9 | 13942 | Level-8 to level-20 , roof | 17 | 11392 | 25334 |  |  |  |  | 8 |  |  | 7 |  |  | Upto Pod 5 done, Pod 5 High Lvl b, 1 Done | level-2,3 |  |  | Nil |  |  | lvl 2 on 24/01 | To update | To update | To update | To update | To update | To update | Running | 1 | 2026-10-01
19 | 250 | AK-25-070 | Ravi | Sattish | Kandan Narayansamy | 1 | DSCA Luminar 2-(151731) | Luminar 2 - (151731) PLOT NO. JVT02HHRA002A | JVT, Dubai | 25375 | P1 - P5, P5 High Level, 1, 2-19, R | 26 | Podium-1 to podium-5, level-1 to level-6 | 11 | 13531.3 | level-7 to level-19, roof | 15 | 11843.7 | 25375 |  |  |  |  | 7 |  |  |  | 6 done |  | upto lvl 2 done | 3,4,5,6 |  |  | Nil |  |  | Lvl 1 on 24/01 | To update | To Update | To update | To update | To update | To update | Running | 1 | 2026-10-01
20 | 251 | AK-25-061 |  |  |  |  | DSCA - | 3343016 | Satwa, Dubai | 20649 | P1,P2,1 to 8, Roof | 11 | [5 empty] | 20649 | 20649 | [24 empty] | TO START
21 | 253 | AK-25-089 |  |  |  |  | Allied Cont. B+G+M+4+R | 1170518 | Al Murar | 5774 | G, M, 1-4, R, UR | 8 | [5 empty] | 5774 | 5774 | [24 empty] | TO START
22 | 255 | AK-25-133 |  |  |  |  | MUNAWEL INTERIORS Strengthening |  |  |  | Strengthening | [7 empty] | 0 | [17 empty] | To update | [6 empty] | Strengthening
23 | 258 | AK-25-018 | Ravi | Sattish | AYYAPPAN ATHAIMOOLAM + Surendra BABU | 2 | ITAL TECH Samana B+G+4P+27+PH.FR (Hilal Conslt) - BV01 | 6453275 | Wadi Al Safa 3, Dubai | 72057 | G, 1p to 4P, 1-27, R, LR | 33 | GF, Podium-1 to Podium-4, 1 - 4 | 9 | 28035 | Level-5 to level-27, ph flr | 24 | 44022 | 72057 | [7 empty] | 4 pt 1 |  |  | GF, P1, P2, P3 Done | PODIUM-4, LEVEL-1, 2,3,4 |  |  | Nil |  |  | Pod 4 on 24/01 | To update | To update | To update | To update | To update | To update | Running | 1 | 2026-12-01
24 | 259 | AK-25-074 | Sadayappan | Raman/ Sadayappan | MARIMUTHU PARAMASIVAM + Akash Velu | 2 | ITAL TECH Samana B+G+P+11+R (AREC) | 6854457 | IMPZ Prod City, Dubai | 23791 | G, P, 1-11, R | 14 | GF, P, 1-11, Roof Zone1 | 13.5 | 23000 | Roof Zone 2 | 0.5 | 791 | 23791 |  |  |  |  | roof zone 2 |  |  | 11th zone 2 |  |  | GF, P, 1 - 7 done | 8 to 11, R-Z1 |  |  | NIL | All Floors Balance | - | Level 6 on 24/01/26 | To Update | To Update | Level 4 | NIL | NIL | NIL |  |  | 2026-06-01
25 | 269 | AK-25-190 | Sadayappan | Raman/ Sadayappan |  |  | Tiger Al Furjan 7 | AFRA033 | JABAL ALI FIRST 591 | 32011 | P1, 1-10, Roof | 12 |  |  |  | P1, 1-10, Roof | 12 | 32011 | 32011 | [24 empty] | TO START
26 | 269 | AK-25-190 | Sadayappan | Raman/ Sadayappan |  |  | Tiger Al Furjan 8 | AFRA028 | JABAL ALI FIRST 591 | 20339 | P1, P2, 1-11, R | 14 |  |  |  | P1, P2, 1-11, R | 14 | 20339 | 20339 | [24 empty] | TO START
27 | 273 | AK-25-093 | Sadayappan | Sadayappan | Kandasamy+ Sivasankar + RAMKI MANIKKAM + Ramar Sadayan + Suresh Malboni | 5 | Atcon Construction + Chawla Architects | 673-1296 | Arjan, Dubai | 194707 | M, P1,P2,1-26, R | 30 | Podium 1 LEVEL - B1,B13,B17,B19,B14; |  | 5944 | M, P1,P2,1-26, R | 30 | 188763 | 194707 |  |  | Pod1-B16 | pod1-B9, | Pod1-B5 |  |  | Pod1 -B17,B19, B1 | Pod1-B1 DONE |  |  | Pod1-B1 | [12 empty] | TO START |  |  | Feb, 2026
28 | 274 | AK-25-185 | Sadayappan | Raman |  |  | Tekton Construction + Renaissance conslt | RA-28 | Dubai South | 7543 | 1, 2, 3-4, R, TR | 6 | 1-4,R | 5 | 7317 | TR | 1 | 226 | 7543 |  |  |  |  | Project HOLD | [5 empty] | 1, 2 done | 3, 4, Roof |  |  | TO DO | All Floors Balance | - | Upto Roof on 24/01/26 | To Update | To Update | Level 4 | Nil | Nil | Nil |  |  | 2026-02-01
29 | 275 | AK-25-243 | Sadayappan | Dharmendran |  |  | MIAMI Contr + Modular design consult | 6181293 | Nad Al Shiba, Dubai | 5242 | 1, 2, 3, 4, 5, R | 6 | 1,2,3, 4, 5 | 5 | 4673 | R | 1 | 566 | 5239 |  |  |  |  | Roof | ON HOLD |  |  |  |  | Lvl 3, 4, 5 |  |  |  | To Do | All Floors Balance |  | upto 5 on 24/01 | To update | To update | To update | To update | To update | To update |  |  | 2026-01-01
30 | 281 | AK-25-230 |  |  |  |  | Baron Contracting + Model Engg Consult | AFC047B | Al Furjan, Dubai | 8123 | P1,P2, 1 to 9, Lroof | 12 |  |  |  | P1,P2, 1 to 9, Lroof | 12 | 13382 | 13382 | [24 empty] | TO START
31 | 282 | AK-24-598 | Sadayappan | Sadayappan |  |  | Modern Cube Contr + Bait Alomor PMC | 2440220 | Muhaisanah Third, Dubai | 1016 | 1st, Mezz, R | 3 | 1 | 1 | 380 | MEZ, R | 2 | 636 | 1016 | [8 empty] | 1 done |  |  | 1 | [5 empty] | Advance | Advance | Nil | Advance | Nil | Nil | 0 |  |  | 2026-03-01
32 | 283 | AK-25-305 |  |  |  |  | Grand Signature bldg. Paramjit | 5130313 Mr. Paramjit | Saih Shuaib 1, Jebel Ali Hills, Dubai | 1350 | GF, 1st, RF | 3 |  |  |  | GF, 1st, RF | 3 | 1350 | 1350 | [24 empty] | TO START
[7 empty] | Grand Signature bldg. Rishi | 6316642 Mr. Rishi | Saih Shuaib 1, Jebel Ali Hills, Dubai | 2087 | GF, 1st, RF, UR | 4 |  |  |  | GF, 1st, RF, UR | 4 | 2087 | 2087 | [24 empty] | TO START
33 | 284 | AK-25-354 | Sadayappan | Raman |  |  | Loft Contracting 3B+G+12+R | 6488529 |  | 35543 | B3,B2,B1,GF, 1-11, LR | 16 |  |  |  | B3,B2,B1,GF, 1-11, LR | 16 | 35543 | 35543 | [24 empty] | TO START |  |  | 2026-03-01
34 | 285 | AK-25-343 | Ravi | Hanifa |  |  | B+G+1+R Teraciel P396-R67 | R67 | Emirates Hills | 2372 | GF, 1st, R, UR | 4 |  |  |  | GF, 1st, R, UR | 4 | 1985 | 1985 | [24 empty] | TO START
35 | 286 | AK-25-211 |  |  |  |  | Model P762 G+2p+12+R |  | Dubai Islands, Dubai | 28467 | P1, P2, 1-12, R | 15 |  |  |  | P1, P2, 1-12, R | 15 | 28467 | 28467 | [24 empty] | TO START
36 | 287 | AK-24-199 | Ravi | Hanifa | MURUGAN CHANDIRAN | 1 | Ritz Contracting | RC-50, | Dubai Residential City | 6368 | 1, 2, 3, 4, HC | 5 | 1, 2 | 2 | 2527 | 3,4,HC | 3 | 3841 | 6368 | [6 empty] | 2 |  |  |  |  | 1 | [5 empty] | Advance | [6 empty] | Running | 1 |  | 2026-02-05
37 | 288 | AK-25-368 | Sadayappan | Raman |  |  | Loft Contr. B+G+6+R | 5310414 | Saih Suhaib 2, Dubai | 12501 | B, G, 1-5, LR | 8 |  |  |  | B, G, 1-5, LR | 8 | 12501 | 12501 | [24 empty] | TO START |  |  | 2026-03-01
38 | 289 | AK-25-303 |  |  | STRENGTHENING |  | SS Lootah Contracting | 3323734 | Pearl Jumeirah, Dubai | 369 | 1st | 1 |  |  |  | 1st | 1 |  | 0 | [24 empty] | TO START
39 | 291 | SK-24-282 |  |  |  |  | G+2+R AL MAERAJ | JPMVIL 071-072 | JUMEIRAH PARK | 1227 | 1st, 2nd | 2 |  |  |  | 1st, 2nd | 2 | 1227 | [25 empty] | TO START
40 | 292 | AK-25-347 |  |  |  |  | G+3P+19+R Model | 6727693 | Barsha South Sci Park | 28863 | P1 to P3, 1 to 19, L Roof | 23 |  |  |  | P1 to P3, 1 to 19, L Roof | 23 | 28863 | 28863 | [24 empty] | TO START
41 | 295 | AK-24-575 | Sadayappan | Raman | Praveen Ganeshan | 1 | UG+G+5P+32 Al Hikma Bldg cont | JVC15CHRA003 | JVC, Dubai | 39865 | P1 to P5, P5 High lvl, 1-32, Roof | 39 | Pod1 to P5, P5 High Lvl, | 6 | 12253 | 1-32, Roof | 37 | 27612 | 39865 |  | upto lvl 2 |  | 1st low lvl |  |  |  | Pod 5 Low lvl |  | p2 low | p1 | P2 to P5 |  |  | Pod 1 to do | Pod 1 | - | P1 Pt1&Pt2 on 24/01 | To Update | Pod 1 | Advance | Nil | Nil | Nil | Running | 1
42 | 296 | AK-25-466 |  |  | STRENGTHENING |  | City Experts | [11 empty] | 0 | [24 empty] | Strengthening
43 | 297 | AK-25-224 | Sadayappan | Sadayappan |  |  | Al Saad Bldg cont | 6714172 | Al Barsha South | 1120 | 1st, Terrace | 2 | 1 | 1 | 532 | Terrace | 1 | 588 | 1120 | [10 empty] | 1 | [6 empty] | To Update | To Update | To Update | To Update | To Update | To Update | To Update |  |  | 2026-02-01
44 | 298 | AK-25-439 | Ravi | Moustafa |  |  | Injaz Al Madina | 1271337 | Hor Al Anz | 38341 | 1st, 2nd, Roof, T Roof | 4 |  |  |  | 1st, 2nd, Roof, T Roof | 4 | 38341 | 38341 |  |  |  |  | lvl 1 pt 1- 4 |  |  |  | lvl 1 pt 5 to 8 | lvl 1 pt 5 to 8 | [14 empty] | Running | 1 | 2026-03-01
45 | 300 | AK-25-471 | Ravi | Sattish |  |  | G+2 Villa, Kanzalard Bldg C |  | Al Awir, Dubai | 806 | 1, LR, UR | 3 | first+second floor | 2 | 723.66 | top roof | 1 | 82.34 | 806 | [10 empty] | 1, Roof | [6 empty] | To Update | To Update | To Update | To Update | To Update | To Update | To Update |  |  | 2026-02-01
46 | 301 | AK-25-229 |  |  |  |  | Model Engg | RC-71 | Dubai South | 6613 | 1-4, R, Roof Deck, U. Roof | 7 | [6 empty] | 0 | [24 empty] | TO START
47 | 302 | AK-25-472 | Sadayappan | Dharmendran | Perisamy Kannan + Prem Kumar | 2 | Shaanxi | 1010432 | Dubai Islands, Dubai | 14896 | P1, P2, SPool, 1-10, Roof | 14 | Pod 1, Pod 2,sw.pool, 1-5 | 8 | 9910 | 6-10, Roof | 6 | 4986 | 14896 |  |  |  |  | 6 |  |  |  | 5 DONE | LVL 1 | Pod1,2, LVL 2 | 3,4,5 | [5 empty] | Claimed upto Pod 2 | To update | To update | To update | To update | To update | To update | Running | 1 |  | 2025-12-18
48 | 303 | AK-25-453 | Ravi | Ravi | Mahtesh | 1 | ACUBE CELESTIA TOWER | 6821286 | Dubai Sports City | 15959 | P1, P2, P3, P4, 1-18, Roof | 23 | P1, P2, P3, P4-Pt1 | 3.3 | 6300 | p3 p-2, p4, 1-18, Roof | 19.7 | 9659 | 15959 | [8 empty] | Pod4 Pt 1 Done |  | P1, P2, P3, | Pod4 Pt 1 | [5 empty] | To update | To update | To update | To update | To update | To update | To update | Running | 1 | 2026-01-20
49 | 304 | AK-25-095 |  |  | STRENGTHENING |  | DNA | [11 empty] | 0 | [24 empty] | Strengthening
50 | 305 | AK-25-451 |  |  |  |  | Injaz Al Madina 3-2 | 555 GOV | Al Majaz 03 | 7379 | Pkg1, Pkg4, 1-11, R | 14 |  |  |  |  | 14 | 7350 | 7350 | [24 empty] | TO START
51 | 306 | AK-25-452 | Ravi | Moustafa |  |  | Injaz Al Madina 3-3 | 439/689 | Mahata | 9221 | P1 to P5, 2-12, R | 16 | P1,P2, P3, P4.pa5 | 4 | 2858.5 | P5,2-12,R | 12 | 6900 | 9758.5 |  |  |  | 1st |  | pod 2, |  |  | P6 Pt1, Done & Pt 2 Prog |  | Pod 2, 3, 4 | [6 empty] | To update | To update | To Update | To Update | To Update | To Update | To Update | Running | 1 | 2026-07-01
52 | 307 | AK-25-222 |  |  |  |  | Aashiyana_Jadaf | 3260962 | Al Jadaf, Dubai | 8870 | P1, P2, P3, 1-9, R | 13 |  |  |  |  | 13 | 8870 | 8870 | [24 empty] | TO START
53 | 309 | AK-25-254 | Ravi | Sattish | Muthu Marimuthu + Surender Kumar | 2 | Luxridge Contracting | 6730108 | Al Barsha South 2ND | 83755 | P1, P2,P3, 1-16, LR, TR | 21 | podium-1, 2 full complete, podium-3(part-1,2,3,3a,4, 6), level-1 (part-1,2,3,3a), lvl 2 pt1,2,3; lvl3 pat,1,2,3; lvl pt 1,2,; lvl 4 Pt1,2,3); lvl 5(Pt1,2,3) | 6 | 38334 | podium-2(part-6,8), podium-3(part-5,6,7,8), level-1 (part-4,5,6,7,8) | 15 | 45421 | 83755 | [10 empty] | pod1, pod2 pt1,2,3,3a,4,5,6,7; pod3 pt1,2,3,3a; lvl 1 pt1,2,3,3a; (lvl2&3 pt1,2,3); | (lvl 4 & 5 pt 1,2,3); pod 2 pt 8; pod 3 pt 4,5 | [5 empty] | Lvl1 Pt1,2,3,3A, Pod 1 Pt5,6,7; Pod 2 Pt4&5 on 24/01 | To update | Recevied | To Update | To Update | To Update | To Update | Running | 1 | 2026-08-01
54 | 311 | AK-25-609 | Ravi | Moustafa | Ramesh Kannan | 1 | B+G+2P+21 Al Masood Nat | 6488722 | Barsha | 29133 | GF, P1, P2, 1, Attic, 2 - 21, R | 25 | GF, P1, P2,1 -7-8-9 | 10 | 15639.39 | 10 TO ROOF | 13 | 11683.24 | 27322.63 |  |  |  | lvl 15 |  |  |  |  | lvl 13 done |  |  | upto lvl 12, 13 | [5 empty] | upto lvl 4 on 24/01 | To update | To Update | To Update | To Update | To Update | To Update | Running | 1 | 2026-07-01
55 | 313 | AK-24-656 | Sadayappan | Dharmendran | Pappu Chunnu Prasad | 1 | G+5P+35+R TAK CONST | 6817403 | Al Barsha South 4th | 36952 | P1-P5, 1-35, R | 41 | Pod1, Pod2 Pt-1,2; POD 3 PT1, POD 4 PT 1, POD 5 PT 1 | 3.5 | 2749 | P1-P5, 1-35, R | 37.5 | 35290 | 38039 |  |  |  | 1ST PT 1 | POD2 PT3 |  |  | POD PT2 |  |  | POD PT1 | Pod2 Pt-1,2; POD 3 PT1, POD 4 PT 1, POD 5 PT 1 | [12 empty] | Running | 1 |  | January, 2026
56 | 314 | AK-25-209 | Sadayappan | Raman/ Ravi | Pankaj | 1 | G+P+5+R Crystal Cont | IC3-B-39 | Warsan 4th, Dubai | 9553 | P, 1-5, LR | 7 | P,1,2, 3, 4, 5 | 6 | 8633 | LR | 1 | 920 | 9553 | [10 empty] | 1 to 5 |  |  |  | Nil | P,1,2,3,4 | - | 4 on 24/01 | To Update | To Update | 3 | Nil | Nil | Nil | running | 1 | 2026-04-01
57 | 315 | AK-25-481 |  |  | MODEL ENGG |  | G+2P+12 Resi Bldg | 1010337 | Dubai Island | 22981 | P1, P2, 1-12, LR | 15 |  |  |  | P1, P2, 1-12, LR | 15 |  | 0 | [24 empty] | TO START
58 | 317 | AK-25-415 | Sadayappan | Raman | Ram Bahadur | 1 | B+G+5 Naf Cont | C13-H-27 | Warsan 4th, Dubai | 10393 | GF, 1, 2-4, 5, LR, UR | 8 | Gf, 1 to 3 | 4 | 4928 | 4,5,LR,UR | 4 | 5465 | 10393 | [6 empty] | 3 PT 2 |  | 3 PT 1 BAL | 2, 3 PT 1 | GF, 1 | [7 empty] | To Update | To Update | Advance | Nil | Nil | Nil | Running | 1 |  | January, 2026
59 | 318 | AK-25-286 |  |  | STRENGTHENING |  | Atcon Arena Towers | [11 empty] | 0
60 | 319 | AK-24-601 | Sadayappan | Dharmendran | Donga Venkat + Anand Make | 2 | Hassan Allam Const RAK |  | Marjan Island, RAK | 31638 | 1, Roof | 2 | 1ST PT1,2; | 0.5 | 8099 |  | 1.5 | 23539 | 31638 |  |  |  |  | 2ND PT1,2 |  |  |  | 1ST PT1,2 DONE | 1ST PT 2 | 1ST PT 1 | [8 empty] | To update | To update | To update | To update | 1st floor Mtrl | Running | 1 |  | 2026-01-25
61 | 320 | AK-25-116 | Ravi | Ravi | Palanisamy Pachamuthu | 1 | B+G+1 Villa Jessr Cont | 3121 | Aalia | 1938 | 1st, Roof | 2 | 1 | 1 | 989 | Roof | 1 | 949 | 1938 | [8 empty] | 1 done | level 1 | [7 empty] | To Update | [6 empty] | Running | 1 |  | 2026-01-25
62 | 321 | AK-24-628 | Ravi | Sattish |  |  | Walk Thru Contracting | 6489154 | Abu Dhabi. Jubail | 1679 | GF, 1, 2, R | 4 | Ground floor, 1st | 2 | 860 | level-2, roof | 2 | 819 | 1679 | [10 empty] | 1 | GF | [12 empty] | Running | 1
63 | 322 | AK-25-688 |  |  |  |  | Golden Wall Villa 26 | P-07-026 | Zorah Dev, Ajman | 880 | BC, GF, RF | 3 |  |  |  |  | 3 | 880 | 880
64 | 323 | AK-25-550 | Sadayappan | Dharmendran |  |  | G+4+Roof, BIN Malek | 643-9765 | Liwan, Dubai | 2218 | 1,2, 3, 4, Roof | 5 |  |  |  |  | 5 | 2219 | 2219 | [24 empty] | To Start |  |  | 2026-03-01
65 | 324 | AK-25-724 |  |  |  |  | G+B+4P+26F+R Model Engg | JVT02IHRA100 | Al Barsha South 4th | 51500 | [8 empty] | 0
66 | 325 | AK-25-405 |  |  |  |  | G+P+12F TA + 12F TB | AFC037A, 037B | Jabal Ali 1st-591 | 28131 | P, 1 TO 12, R | [5 empty] | 14 | 23843 | 23843
67 | 326 | AK-25-632 |  |  |  |  | G+2P+8 AECS | DIA-RE-0183 | Dubai Island | 14311 | UG, G, P1, P2, 1-8, LR | 13 |  |  |  |  | 13 | 14311 | 14311
68 | 327 | AK-25-351 | Ravi | Ravi | VENKATESAN VADAMALI | 1 | SS Lootah Contracting | 2610787 | Muhaisnah First, Dubai | 8651 | 1, 2, R, TR | 4 | 1,2 | 2 | 5403 | R, TR | 2 | 3248 | 8651 | [10 empty] | 1, 2 | [13 empty] | Running | 1 | 2026-02-01
69 | 328 | AK-25-213 | Sadayappan | Raman/ Sadayappan |  |  | Private Villa Al Abbar | 3370207 | Zabeel 2, Dubai | 4212 | 1, Roof | 2 |  |  |  |  | 2 | 4212 | 4212 |  |  | 1 | [21 empty] | Running | 1
70 | 329 | AK-25-715 |  |  | MODEL ENGG |  | B+G+P+9 RAK | MRA-55 & MRA-57 | Al Marjan Island, RAK | 26247 | [8 empty] | 0
71 | 330 | AK-25-725 |  |  | MODEL ENGG |  | B+G+2P+10+R MODEL | 1010338 | Dubai Island | 21500 | G+2P+12 | [7 empty] | 0
72 | 331 | AK-25-761 | Ravi | Sattish |  |  | DHCN G+4 | JVC13IMRA005 | JVC, Dubai | 8315 | 1-4+R | 5 | 1 | 1 | 1746 | 2,3,4,R | 4 | 6569 | 8315 | [7 empty] | 1 | [16 empty] | Running | 1
83 | 332 | AK-25 |  |  |  |  | AL BAIT ENG CONSLT | [11 empty] | 0
84 | 333 | AK-25-689 | Ravi | Sattish | ANNAMALAI ANNADURAI | 1 | BARARI VIEWS 2 SAMANA BV 02 | 6453275 | Wadi Safi, Barari | 71787 | GF, P1 to P4, 1 to 27, R, Lift R | 35 | GF,P1 TO P4; | 5 | 18560 | level-1 to level-27, ph floor | 30 | 53227 | 71787 | [6 empty] | pod4 z1 | pod4 z2; |  |  | upto pod 2 | pod3 | [5 empty] | GF on 24/01 | To update | To Update | To Update | To Update | To Update | To Update | Running | 1
85 | 334 | AK-25-810 |  |  |  |  | AMMON CONTRACTNG | 6313268 | Hadaeq Shk Mohd Bin Rashid | 2118 | Basement, Foundation | 2 |  |  |  |  | 2 | 2118 | 2118
86 | 335 | AK-25-708 | Sadayappan | Dharmendran |  |  | RAK Academy - Chicago | 602014004 | Marjan Island, RAK | 9306 |  |  | SPORTS BLDG 1, 1ST PT1 |  | 800 |  | 6 | 8506 | 9306 | [5 empty] | SPORTS 1ST PT1 | [5 empty] | SPORTS 1ST PT1 | [5 empty] | To update | To update | To update | To update | To update | To update | To update | Running | 1 |  | 2026-01-15
87 | 336 | AK-25-495 | Ravi | Moustafa |  |  | B+G+13 Design Hub DLRC | 6488673 | Dubai Land Residence Complex | 19547 | GF, 1-13,LR, UR | 16 | [6 empty] | 0 | [24 empty] | Running | 1 |  | 2026-01-10
88 | 338 | AK-25-448 |  |  |  |  | B+G+M & G+1+R Casais | 6188937 | Nad Al Shiba First | 10982 | Pool, GF, 1st, Roof | 4 |  |  |  |  | 4 | 10982 | 10982
89 | 339 | AK-031 |  |  |  |  | SHINE SQUARE | 1170518 | Al Murar, Dubai | 5774 | GF, M, 1-4, R, UR | 8 |  |  |  |  | 8 | 129951 | 129951
90 | 340 | AK-25-089 |  |  |  |  | ALLIED | 1170518 | Al Murar | 5774 | B+G+M+4+R | 8 |  |  |  |  | 8 | 5774 | 5774
91 | 341 | AK-25-487 | Sadayappan | Dharmendran | Venkadeswaran Velu | 1 | 1B+G+2P+15 TAK | AFMU019B | Furjan | 14105 | P1,P2, AM, 1-15 | 18 | P1,P2, AM, 1 | 4 | 4352 | AM, 1-15 | 14 | 9753 | 14105 |  |  | 2 |  |  |  | 1 |  |  |  | Pod1 | P2, AM, 1 | [5 empty] | Advance |  | Advance |  |  | Advance |  | Running | 1 |  | 2026-02-02
92 | 342 | AK-25-752 | Ravi | Moustafa | Islam Saad + Ahmed Farhat | 2 | AL SHAFAR G+3P+19+R | 6820126 | Al Hebiah 4th | 41386 | G+3P+19+R | 25 | GF,P1, P2, P3, 1, 2.3.4.5 | 6 | 14553 | 3-19,R | 16 | 21453 | 36006 | [7 empty] | 9 inprogres |  |  | 6 done | 7, 8 balance |  |  | Nil | P1 to P3 |  | To update | To update | To update | To update | To update | To update | To update | Running | 1 | 2026-08-01
93 | 343 | AK-25-548 |  |  |  |  | AL QAHERA | 5914121 | Jabal Ali 1st | 12015 | Al Furjan 15 Villas | 30 | [5 empty] | 12015 | 12015 | [17 empty] | To update | To update | To update | To update | To update | To update | To update |  |  |  | 2026-01-25
94 | 344 | AK-25-718 |  |  |  |  | AECS | 6854308 | IMPZ Dubai | 53228 | B+G+3P+20 | 25 | [6 empty] | 0
95 | 345 | AK-25-877 | Sadayappan | Dharmendran |  |  | G+4 BIN MALEK | 6439734 | Wadi Al Safa 2 | 2120 | 1-4, R | 5 | [5 empty] | 2120 | 2120 |  |  |  |  | 1 | [19 empty] | Running | 1
96 | 346 | Ak-25-872 | Ravi | Moustafa |  |  | 1B+G+1P+13+R Rabat | 6488736 | Wadi Al Safa 5, Dubai | 18649 | GF, P, 1-13, R, TR | 17 |  |  |  |  | 17 | 18649 | 18649 |  |  |  |  | Pod 1 Maint | [6 empty] | 15 | [12 empty] | Running | 1
97 | 347 | AK-25-759 |  |  |  |  | G+GP+15TYP INJAZ |  | Sharjah | 25400 | [7 empty] | 25400 | 25400
98 | 348 | AK-25-865 |  |  |  |  | B+G+5P+50+R Tiger | A37 | Al Khan, Sharjah | 85565 | P1-P5, 1-50,R, TR | 57 |  |  |  |  | 57 | 85565 | 85565
99 | 349 | AK-25-894 -T1 | Ravi | Moustafa |  |  | 2B+G+M+(15+18+21)+R Tiger Orchid 4,5,6 | 3284 | Ajman | 113559 | B,G,M,P1,P2,P3,1-21,R 3TWR | 28 |  |  |  |  | 28 | 113562 | 113562 |  |  |  | Orch6 - B1 |  | Orch5 B1 Done | [18 empty] | Running | 1
100 | 349 | AK-25-894 -T2 | Ravi | Moustafa |  |  | 2B+G+M+(15+18+21)+R Tiger Orchid 1,2,3 | 3284 | Ajman | 112664 | B,G,M,P1,P2,P3,1-21,R 3TWR | 28 |  |  |  |  | 28 | 112563 | 112563 | [24 empty] | Running | 1
101 | 350 | AK-25-884 | Ravi | Moustafa |  |  | G+3P+13 Golden Bldg Cont. | 1341550 | Al Mamzar, Dubai | 16988 | P1-P3, 1-13, R, UR | 18 |  |  |  |  | 18 | 16988 | 16988 | [5 empty] | Pod 2 Done |  |  |  |  | Pod 1 | [13 empty] | Running | 1 |  | 2026-03-01
102 | 351 | AK-25-837 | Sadayappan | Dharmendran |  |  | G+P+6+R Autolink Nuvana | DIA-RE-0215 | Dubai Islands | 12343 | P,1-6,R,TR | 9 |  |  |  |  | 9 | 12343 | 12343 | [24 empty] | Running | 1
103 | 352 | AK-25-438 | Ravi | Sattish |  |  | G+3P+4+R Al Maeraj Cont. | 6457762 | Wadi Al Safa | 11668 | P1-P3, 1-4, LR, UR | 9 | P1,P2,P3,1 | 4 | 7638 | Level-2 to level-4, roof | 5 | 6620.32 | 14258.32 |  |  | lvl 2 |  |  |  |  | lvl 1 pt1 | lvl 1 pt 2 done |  | PODIUM-1, PODIUM-2 pt1 | pod2 pt2; pod3 | [5 empty] | Advance | Nil | Advance | Nil | Nil | Advance |  | Running | 1
104 | 354 | AK-25-840 | Sadayappan | Raman/ Ravi | TO START |  | B+G+3P+19+R Lux Ridge | 6727770 | Barsha South | 113960 | B,GF,3P,19,R | 24 |  |  |  |  | 24 | 113960 | 113960 | [27 empty] | 2026-02-15
105 | 355 | AK-25-047 |  |  |  |  | 2B+G+10P+37+R Tiger | 3460377 | Business Bay | 108865 | B,GF,P1-P10, 1-37,R, UR, Deck R | 52 |  |  |  |  | 52 | 108865 | 108865
106 | 356 | AK-25-786 | Sadayappan | Dharmendran | EZHUMALAI SAMIDURAI | 1 | G+3P+20F+R TAK Const | 6117273 | Meydan | 26588 |  |  | P1 Pt-1,2; P2 PT1, P3 PT1 |  | 4356 | P1 Pt-2, p2,p3,1to20,R | 0 | 25588 | 29944 | [11 empty] | P1 Pt-1,2; P2 PT1, P3 PT1 | [12 empty] | Running | 1 |  | 2026-02-28
107 | 357 | AK-25-954 | Sadayappan | Sadayappan | Tamil Rasan | 1 | G+2P+6TYP+R Golden Bldg | 6731015 | Barsha South 3 | 10902 | P1,P2,1-6,LR,UR | 10 | P1, P2,1,2, 3, 4 | 6 | 7232 | 5,6,LR,UR | 4 | 3670 | 10902 | [8 empty] | 4 - done |  | P1, P2,1,2, 3, | 4 |  |  | Nil | Pod 1 |  | Pod 2, on 24/01 | To Update | To Update | To Update | To Update | To Update | To Update | Running | 1 |  | 2025-12-20
108 | 358 | AK-25-931 | Sadayappan | Raman/ Sadayappan | Saminathan Pazhni | 1 | G+3P+4+R NAF | 6457759 | Wadi Al Safa 3, Dubai | 18282 | P1 to P3, 1to 4, LR, UR | 9 | P1 - P3, 1 | 3 | 11005 | 2 to 4, LR, UR | 6 | 7277 | 18282 | [7 empty] | 1 PT3,4 | 1ST PT1,2 BAL | P2 | P1 | P3,1ST PT1,2 | [5 empty] | Advance |  | Nil | Advance | Nil | Nil | Nil | Running | 1
109 | 359 | AK-25-758 | Sadayappan | Dharmendran | SENDAMARIA KANDAN | 1 | G+1P+6+R Indo Gulf P189 | DIA-RE-0238 | Nakhlat Deira, Dubai | 9585 | P, 1-6, R | 8 | p1, 1, 2 | 3 | 4330 | 3-6, R | 5 | 5255 | 9585 | [8 empty] | 2 DONE |  | POD 1PT 1 | REST BAL | [12 empty] | Running | 1 |  | 2026-02-16
110 | 360 | AK-25-667 |  |  |  |  | G+8+R NAF | DIA-RE-0194 | Nakhlat Deira, Dubai | 17583 | P1,P2, 1-8,R | 11 |  |  |  | P1,P2, 1-8,R | 11 | 17583 | 17583 | [27 empty] | 2026-04-15
111 | 361 | AK-25-960 | Ravi | Moustafa |  |  | 2B+G+19 CEG CAPITAL ONE |  | Motor City | 45318 | B, G, 1-19, R,TR | 23 |  |  |  | B, G, 1-19, R,TR | 23 | 45318 | 45318 | [24 empty] | Running | 1
112 | 362 | AK-25-904 | Sadayappan | Sadayappan | Rajajrajan Govindraj + Youssef ere garage | 2 | 1-13, ROOF, sola | 5919562 | Jebak ALI 1ST | 36316 | 1-13,R | 14 | 1, 2-Pt1,2 | 1.5 | 6757 | 2-13,R | 12.5 | 29559 | 36316 |  |  | lvl 2 pt 5 |  | lvl 2 pt3,4 |  |  |  | Lvl 2 Pt1,2 bal | [15 empty] | Running | 1
113 | 363 | AK-25-844 |  |  |  |  | CITY EXPERTS | 533496 | Saih Al suhaib, DIC | 5858 | 1,2,3,R | 4 |  |  |  | 1,2,3,R | 4 | 5858 | 5858
114 | 364 | AK-25-955 |  |  |  |  | B+G+4 ARABCO | 5992231 | Jabel Ali Indst 1 | 6121 | 1,2-4, R | 5 |  |  |  | 1,2-4, R | 5 | 6121 | 6121
115 | 365 | AK-25-984 | Sadayappan | Dharmendran | Vinoth Kumar | 1 | HK TWIN TOWER-0137 | DIA-R-0137 | Dubai Islands | 15153 | P1,P2, 1-12, Roof | 15 | P1, P2, 1 | 3 | 6290 | P1,P2, 1-12, Roof | 12 | 8863 | 15153 |  |  |  |  | 2 |  |  | 1 |  |  |  | ALL BAL | [12 empty] | Running | 1
116 | 365 | AK-25-984 | Sadayappan | Dharmendran |  |  | HK TWIN TOWER-0138 | DIA-R-0138 | Dubai Islands | 15152 | P1,P2, 1-12, Roof | 15 | P1, |  | 2107 | P2, 1-12, Roof | 15 | 15154 | 17261 |  |  | POD 2 |  |  |  | POD 1 | [17 empty] | Running | 1
117 | 366 | AK-25-964 |  |  |  |  | TONINI | 6184086 | NADD Al Shiba First | 36910 | Raft, First, Second | 3 |  |  |  | Raft, First, Second | 3 | 21348 | 21348
118 | 367 | AK-25-945 |  |  |  |  | WOODCO | 3621091 |  | 1407 | 1, 2, roof | 3 |  |  |  | 1, 2, roof | 3 | 1407 | 1407
119 | 368 | AK-25-540 | Ravi | Ravi |  |  | FAJA | 6439980 | Wadi Al Safa 2 | 28256 | Parking, 1st, 2nd, 3rd, Roof | 4 |  |  |  | Parking, 1st, 2nd, 3rd, Roof | 4 | 28256 | 28256 | [24 empty] | Running | 1
120 | 369 | AK-25-249 | Sadayappan | Raman/ Sadayappan | Mahendra Kumar | 1 | G+4 RE-22 Uniforce | RE-22 | Dubai South | 6059 | 1, 2-4, Roof | 5 | 1,2,3 | 1 | 3653.68 | 4, R | 2 | 2401 | 6054.68 | [10 empty] | 1, 2, 3 |  |  |  |  | Nil |  | 1st on 24/01 | To Update | To Update | Advance | Nil | Nil | Nil | Running | 1
121 | 370 | AK-25-702 |  |  |  |  | Wedding Hall Aroma | [9 empty] | 0 | 59418 | 59418
122 | 372 | AK-25-1004 |  |  |  |  | 18,19,20, 25, 28, 30, 44, 49 Golden Wall Villas | [10 empty] | 8393 | 8393
123 | 373 | AK-25-1006 | Ravi | Ravi |  |  | G+1+R DIRHAM Cont | 3520509 | Jumeirah 3rd, Dubai | 1283 | 1, Roof, Uroof | 3 |  |  |  |  | 3 | 1284 | 1284 | [24 empty] | Running | 1
124 | 374 | AK-25-881 | Ravi | Moustafa |  |  | DWC AMANA | AC-F-15 | DWC, DUBAI | 5854 | 1,2, Roof, Service Floor | 3 |  |  |  |  | 3 | 5853 | 5853 |  |  |  | 1st Pt 1 | [20 empty] | Running | 1
126 | 376 | AK-25-1062 | Ravi | Hanifa |  |  | G+4 STAFF SAM Bldg Cont. | 599562 | Jebel Ali Indus | 8560 | 1 to 4, Roof | 5 |  |  |  |  | 5 | 8560 | 8560
127 | 378 | AK-25-1023 | Ravi | Sattish |  |  | B+G+8+R Globecon | 6731162 | Al Arjan | 26376 | GF, 1-8, Pool deck, Roof | 11 | GF pt1,2,3 | 0.75 | 3940 | GF pt4, 1-8, Pool deck, R | 10.25 | 22436 | 26376 |  |  | GF pt4 |  |  |  | GF pt3 |  | GF pt1,2 done | GF pt2 | GF pt1 | [13 empty] | Running | 1
128 | 380 | AK-25-1121 | Ravi | Moustafa |  |  | G+2P+ 14TA+14TB MBC | DIA-MU-N01B | Dubai Islands | 30065 | P1, P2 1-14, R | 17 |  |  |  |  | 17 | 30065 | 30065 | [24 empty] | Running | 1
129 | 381 | AK-25-1050 | Sadayappan | Raman/ Sadayappan |  |  | B+G+1 NAF | 5912862 | Jabel Ali | 3170 | GF, 1, 2 | 3 |  |  |  |  | 3 | 3170 | 3170 |  |  |  |  | GF Dm apvd | [19 empty] | Running | 1
130 | 383 | AK-25-1056 | [5 empty] | 3321863 | Pearl Jumeirah, Dubai | 1932 | 1, Roof | 2 |  |  |  |  | 2 | 1931 | 1931
131 | 384 | AK-25-968 | Ravi | Hanifa |  |  | G+6+R Abaj Cont. | RF-01 | Dubai Aviation City | 7024 | 1-6, LR, UR | 8 |  |  |  |  | 8 | 7023 | 7023 |  |  |  |  | 1 | [19 empty] | Running | 1
132 | 385 | AK-25-1117 |  | cancelled |  |  | G+4+R Abaj Cont | RG-54 | Dubai Aviation City | 5391 | 1-4, LR, UR | 6 | CANCELLED PROJECT | [30 empty] | cancelled |  |  | cancelled
133 | 386 | AK-25-763 |  |  |  |  | B+G+9 Jeikor | PJCRC328 | Naklat Jumeirah 381 | 18242 | GF, 1-9, LR | 11 |  |  |  |  | 11 | 18242 | 18242
134 | 387 | AK-24-258 |  |  |  |  | B+G+4P+28+R Jade Tiger | 6457865 | Wadi Al Safa 3 | 58229 | GF, P-P4, 1-28, R | 34 |  |  |  |  | 34 | 58229 | 58229
135 | 388 | AK-25-1126 | Ravi | Moustafa | Ayman (PT Works) PT | 1 | P+G+4F+R InjazM Warsan | 6218416 | Warsan | 5380 | GF, 1-4, R, Main F,R, TR | 9 |  |  |  |  | 9 | 6200.15 | 6200.15 |  |  | 1st | [5 empty] | GF Done | [15 empty] | Running | 1
136 | 389 | AK-25-1045 |  |  |  |  | 2B+G+13+R Autolink Seraph | 6488669 | Wadi Al Safa 5 | 16136 | 1-13, R | 14 |  |  |  |  | 14 | 16136 | 16136
137 | 390 | AK-25-1060 | Sadayappan | Raman/ Ravi |  |  | G+P+6 Ocean Pearl1 | DIA-RE-0203_0204 | Dubai Island | 15525 | 1-6, Roof | 7 |  |  |  |  | 7 | 15525 | 15525 | [24 empty] | Running | 1
138 | 391 | AK-25-1061 | Sadayappan | Raman/ Ravi |  |  | G+P+6 Ocean Pearl2 | DIA-RE-0191_0192 | Dubai Island |  | 1-6, Roof | 7 |  |  |  |  | 7 | 20126 | 20126 | [24 empty] | Running | 1
139 | 392 | AK-25-1097 |  |  |  |  | G+4P+15+R Luxridge | 6727757 | Barsha 2nd | 73475 | 1P-4P, 1LS, 1US, 2 to 15, R,UR | 21 |  |  |  |  | 21 | 72512 | 72512
140 | 393 | AK-25-853 |  |  |  |  | G+4 Janus Model | RE-14 | Dubai South | 9082 | GF, 1-4, LR, UR | 7 |  |  |  |  | 7 | 9082 | 9082
141 | 394 | AK-26-019 |  |  |  |  | G+2P+10+R OST | 4168004 | Nad Al Hammar | 8724 | P1, P2, 1-9 | 11 |  |  |  |  | 11 | 8724 | 8724
142 | 395 | AK-25-1070 |  |  |  |  | G+4P+31+Mech+R Luxridge | 6459906 | Wadi Safa 3 | 210664 | UD, GF, P1-P4, 1-31, R | 38 |  |  |  |  | 38 | 210664 | 210664
143 | 396 | AK-25-704 | Sadayappan | Raman | RAJA ARUMUGAM | 1 | B+G+5+R ROME 1 | 6453224 | WADI AL SAFA | 5911 | 1-5, R, TR | 8 | 1 to 3 | 3 | 2946 | 4,5,R,TR | 5 | 2965 | 5911 | [7 empty] | 3 |  |  | 1,2 | [13 empty] | Running | 1
144 | 397 | AK-25-1089 |  |  |  |  | G+2P+8+R Shine Square | DIA-RE-0226 | DUBAI ISLAND | 15619 | P1,P2,1-8,R | 11 |  |  |  |  | 11 | 15619 | 15619
145 | 398 | AK-25-1101 |  |  |  |  | G+4F+R Loft | 6187552 | NAD AL SHIBA | 10844 | 1-4,R,UR | 6 |  |  |  |  | 6 | 10844 | 10844
146 | 399 | AK-25-766 | Ravi | Ravi |  |  | G+1F Al Awir Belmont | 7117131 | AL AWIR 1ST | 572 | 1, R | 2 |  |  |  |  | 2 | 572 | 572
147 | 400 | AK-26-020 | Ravi | Hanifa |  |  | G+4 Al Maeraj | RG-86 | DUBAI SOUTH | 9297 | UG,GF,1-4,R | 7 |  |  |  |  | 7 | 9295 | 9295
148 | 401 | AK-25-1115 |  |  |  |  | Elton Real Estate (Model) | 6181272 | Nad Al Shiba | [7 empty] | 0 |  | 0
149 | 402 | AK-26-111 | Ravi | Moustafa |  |  | G+1+R Al Harith | 6174755 | Nad Al Shiba | 1211.5 | 1, RF, TR | 3 |  |  |  |  | 3 | 1212 | 1212 | [24 empty] | Running | 1
150 | 403 | AK-26-055 |  |  |  |  | G+5P+15 AL SERH KABEER | 370 | SHARJAH | 13620.84 | 1-4Prkg, 5th prkg, 1-15 typ | 20 |  |  |  |  | 20 | 13621 | 13621
151 | 404 | AK-25-530 |  |  |  |  | G+2P+8F+R FAJA | 3347326 | Jumeirah Garden City, Dubai | 8933 | 1-8,RF, UR | 10 |  |  |  |  | 10 | 8933 | 8933 | [24 empty] | Running | 1
152 | 405 | AK-26-072 |  |  |  |  | G+1 Alpha Matrix | 3470992 | Sobha Hartland | 452.52 | 1, Roof | 2 |  |  |  |  | 2 | 453 | 453
153 | 406 | AK-26-139 | Sadayappan | Raman/ Ravi |  |  | LS Design | 3323893 | La Mer Villa | 1024 | 1, RF, UR | 3 |  |  |  |  | 3 | 1024 | 1024 | [24 empty] | Running | 1
154 | 407 | AK-25-907 | Sadayappan | Dharmendran |  |  | G+M+Services Julfar Masjid | 5310929 | Saih Suhaib | 369 | Mezz, Roof | 2 |  |  |  |  | 2 |  | 0 | [24 empty] | Running | 1
155 | 408 | AK-25-615 |  |  |  |  | G+1P+8TYP+R Mothaberoon | DIA-RE-0209 | Dubai Island | 11880 | P, 1-8, Terrace RF | 10 |  |  |  |  | 10 | 11880 | 11880
156 | 409 | AK-25-852 |  |  |  |  | B+G+4+R MODEL | 6456563 | Wadi Al Safa 3 | 16426 | [8 empty] | 0
157 | 410 | AK-25-480 |  |  |  |  | 3B+G+3P+20 MODEL | [11 empty] | 0
158 | 411 | AK-26-057 | Ravi | Hanifa |  |  | TERRA HEIGHTS EAST COAST | 1B | EXPO LIVING, DUBAI | [8 empty] | 95338 | 95338
159 | 412 | AK-24-064 |  |  |  |  | G+4P+6 LOFT | 3341042 | [10 empty] | 0
160 | 413 | AK-25-1043 |  |  |  |  | B+G+4+R CONVRGNT |  | DUBAI SOUTH | [7 empty] | 5 | 14558 | 14558
161 | 414 | AK-26-154 |  |  |  |  | G+2P+7TYP+R AL SERH K | 6850754 | MEÁISM 1ST | [7 empty] | 10 | 13824 | 13824
162 | 415 | AK-26-096 |  |  |  |  | G+4 SKADA | RC61 | DUBAI SOUTH | [7 empty] | 5 | 7154 | 7154
163 | 416 | AK-24-623 |  | Strengthening |  |  | 606 HI BEAM | [11 empty] | 0
164 | 417 | AK-25-915 |  | Strengthening |  |  | NEXT ENGG 7 TIDES | [11 empty] | 0
165 | 418 | AK-25-705 | Sadayappan | Raman/ Ravi |  |  | B+G+5+R ROME 2 SAMANA | 6453236 | NAD AL SHEBA | 5840 | 1-5, R, TR | 7 |  |  |  | 1-5, R, TR | 7 | 5840 | 5840 |  |  |  |  | 1 | [19 empty] | Running | 1
166 | 419 | AK-26-012 |  |  |  |  | 2B+G+8+R SAMANA BUSS PARK | 6457794 | WADI AL SAFA 3 | 22935 | B1+GF+1 - 8, R, TR | 12 |  |  |  |  | 12 | 22935 | 22935
167 | 420 | AK-26-152 |  |  |  |  | G+2P+12 KATA DORA ITEC | 5912880 | Jabel Ali First, Dubai | 38547 | 1P, 2P, 1-12, RF | 15
168 | 421 | AK-26-261 |  |  |  |  | EMIRATES ORBIT G+MEZZZ | 71111392 | Al Awir, Dubai | 888
169 | 422 | AK-26-259 |  | SCANNING |  |  | BATHROOM
170 | 423 | AK-26-263 |  |  |  |  | G+2+R BLACK TULIP | 1341501 | Al Mamzar, Dubai | 1255 | 1, ROOF, TR | 3
171 | 424 | AK-26-300 | Sadayappan | Raman/ Ravi |  |  | 3B+G+12+R SHINE SQUARE | IC3-01.01 | Warsan fourth | 15991 | 1-11, TERRACE | 12 | 1 | 1 | 1608 | 2-11, TERRACE | 11 | 14383 | 15991 | [10 empty] | 1 | [13 empty] | Running | 1
172 | 425 | AK-26-276 |  |  |  |  | B+G+2, 2 TOWERS A 20 & TOWER B 19 FLOORS TURATH AL ASEEL | DHE-PA15.002 | DUBAI HILLS | 67000
173 | 426 | AK-25-777 |  |  |  |  | 3B+G+21 SAMANA | 6854333 | ME'ALISEM 1ST | 41494 | 1-21, ROOF | 22
174 | 428 | AK-25-800 |  |  |  |  | G+4 CALGARY PROPERTIES | RC-73 | DUBAI SOUTH | 7937 | GF, 1-4, ROOF | 6
175 | 429 | AK-26-369 |  |  |  |  | 2B+G+13F+R Razanco | 6488632 | Dubailand | 21255 | 1-13, R, UR | 15
176 | 430 | AK-26-299 |  |  |  |  | G+P+9 TYP+R Al Serh Kabeer Mina | B8.01.08 | Mina Rashid | 18150 | P, 1-9, R | 11
177 | 431 | AK-26-275 |  |  |  |  | G+5P+15TYp Al Serh Kabeer Shj | A52 | Sharjah | 21651 | 1st to 4th Prkg, 5 lwr Prkg, 5 Upr Prkg, 1-10, R | 16
| 432 | AK-26-435 | Sadayappan | Dharmendran |  |  | G+2P+12 BJORG | 1010337 | Dubai Island | 23984 | P1, P2, 1-12, LR | 15
179 | 433 | AK-26-392 |  |  |  |  | HAO Arch. | 6854445 | Impz G16 | 22082 | B, GF, 1-8, UR | 11
180 | 434 | AK-26-396 |  |  |  |  | HAO Arch. 130 | 6730130 | Al Barsha | 33789 | P1, P2, 1-6, Terrace | 9
181 | 435 | AK-26-384 | Ravi | Sattish |  |  | B.G+G+5P+20+R, Luminar 3 | 1341562 | Al Barsha | 25676 | P1-P5, 1-20, R | 26
182 | 436 | AK-26-336 |  |  |  |  | G+5+R RES. & COMM. Bldg Miami | 6181335 | NADD Al Shiba | 5530 | 1-5, Roof | 6
183 | 437 | AK-26-059 |  |  |  |  | G+4+R AMVIN GROUP | R67 | DUBAI SOUTH | 7373 | 1-4, R | 5
184 | 438 | AK-26-373 | Ravi | Sattish |  |  | C-31; 2B+G+15+R+TR BURTPLACE | YS2-17 | YAS Island | 28041 | 5-15, R | 11
185 | 439 | AK-26-410 |  |  |  |  | F-06; 1B+G+9+R BURTPLACE | SE45_02 - C14 | Khalifa City, AD | 45280 | 1-9, R | 10
186 | 440 | AK-26-353 |  |  |  |  | B+G+6 THK CONSTR | 5310414 | SAIH SHUAIB 2 | 13835 | B,G,1-5,LR | 8
187 | 441 | AK-26-245 |  |  |  |  | B+G+7 FLORA ISLE | 1010608 | DUBAI ISLAND | 37108
[5 empty] | TOTAL | 67 |  |  | TOTALS | 4014596.96 |  |  |  |  | 736761.03 |  |  | 2843752.96 | 3579286.99 | [25 empty] | 71
[7 empty] | Completed | New Projects | Ongoing Projects |  | NEED UPDATE |  | Contractor TBA
Projects running with movable manpower
MANPOWER REQUIRED
[6 empty] | S. No. | PT Manpower Vacation List
[7 empty] | NAME | ETA | To Project
[6 empty] | 1 | Suresh Kandan
|  | Total Site Staff |  |  |  | 2 | Praveen
|  | With Eng Islam Civil Works |  |  |  | 3 | Aiyyappan
|  | With Eng Mamdouh |  |  |  | 4 | Muthu Maya Kanan | 2026-06-18
|  | Vacation |  |  |  | 5
|  | TYCOON |  |  |  | 6
|  | Current PT Staff |  |  |  | 7
Actual Site Total PT STAFF
62

## COMPL-PARTL-PROJECT LIST
PROJECT LIST
S. No. | Folder No. | AK Job No. | Project Management Details | Project Details |  |  | Tender NET Area | PT SLAB DETAILS |  | PT Slabs Concreted Details |  |  | GROUTING STATUS | CLOSEOUT DOCUMENTS
|  |  | Engineer | Project Name | Plot No | Location |  | Description | Nos. | Slabs | Nos. | Area |  | As Built Drawing Last completed level | As Built Drawing Balance to do | Submission Status | Project status
1 | 63 | AK-22-093 | Sattish | Abdel Aziz Al Majid | 671-669 | Al Bu Daniq, Sharjah | 28267 | P1 to P4, Up Pod, 1st to 15, R | 21 | P1 to P4, Up Pod, 1st to 15, R | 21 | 28267 |  |  |  |  | Completed
2 | 121 | AK-23-256 | Dharmendran | JULFAR CONTRACTING PLOT 003 | JVC13LHRS003 | JVC, Dubai | 25440 | GF, P1,P2,P3, 1 to 23, Roof | 28 | GF, P1,P2,P3, 1 to 23 | 27 | 25440 |  |  |  |  | Completed
3 | 127 | AK-23-368 | Hussein | Aroma JVT | JVT03GHRA001 | JVT, Dubai | 33094 | P2,P3,P4, 1 to 24, Roof | 28 | P2,P3,P4, 1 to 24, Roof | 28 | 33094 |  |  |  |  | Completed
4 | 134 | AK-23-378 | Dharmendran | TAK Contracting_IGO G+M+3P+48 | 3450395 | Burj Khalifa, Dubai | 71283 | M, P1 to P3, 1 - 48, RMech01, RMech02, TR | 56 | M, P1 to P3, 1 - 48, Mech 1,2,TR | 56 | 71283 |  |  |  |  | completed
5 | 145 | AK-23-247 |  | Benz Contracting | RS-3C23(ADM), S3-C34(SHAMS) | Abu Dhabi | 38163 | P1toP4, 1-19, Roof, Roof | 25 | P1toP4, 1-19, Roof, | 25 | 38163 |  |  |  |  | Completed
6 | 146 | AK-24-381 | Sattish | 5912278 | Jabel Ali First, Dubai | 17690 | Raft, GF, P1, P2, 1st, 2to14, Roof | 19 | Raft, GF, P1, P2, 1 to 14, Roof | 19 | 17690 | - |  |  |  |  | Completed
| 154 | AK-24-127 |  | SBM-Strengthening
7 | 155 | AK-24-12 | Hussein | Gulf Modern Contracting-4 villas | 3435484-507-491-506 | Al Wasl, Dubai | 5780 | GF to Top Roof, 4 Villas |  | Completed |  | 5780 |  |  |  |  | Completed
8 | 158 | AK-23-471 | Sattish | Heilbron_G+P+5 Jumeira JVC | JVC11IMRP002 | JVC, Dubai | 15605 | Raft, P, 1 to 5, Roof | 8 | Completed | 8 | 15605 |  |  |  |  | Completed
9 | 159 | AK-24-74 | Raman | Jams Contracting |  | Business Bay, Dubai | 23906 | P1, P2, P3, 1-15, R | 19 | P1, P2, P3, 1-15, R | 19 | 23906 |  |  |  |  | Completed
10 | 160 | AK-23-330 | Sattish | Sarah Cont Mohsin Villa-Model | 6316728 | Dubai Hills | 1310 | GF, 1, LR, R | 4 | GF, 1, LR | 3 | 1261 |  |  |  |  | Completed
11 | 164 | AK-23-359 | Sattish | Object 1(DSCA) | JVC12PHRS005 | JVC, Dubai | 24105 | P1,P2,P3, P3-Upper, 1-22, R | 27 | P1,P2,P3, P3-Upper, 1-22, R | 27 | 24105 |  |  |  |  | Completed
12 | 167 | AK-23-224 | Sattish | TPC DHCN contracting | 1C1-CBD-33 | Warsan, Intl City | 13073 | 1-10, Roof | 11 | 1-10, | 11 | 13073 |  |  |  |  | Completed
13 | 170 = 118 | AK-23-339 | Dharmendran | Thappar G+1+R | 3940195 R39 | Al Thanyah fourth | 2741 | Gf, FF, LR, Lrdeck | 4 | Gf, FF, LR, Lrdeck | 4 | 2741 |  |  |  |  | Completed
14 | 174 | AK-24-40 | Raman | B+G+1+R Villa Model Cons | 6181340 | Merkadh | 4003 | GF, 1st, 2nd, Roof | 4 | Gf, 1st.2nd, R | 4 | 4003 |  |  |  |  | Completed
15 | 173 | AK-24-252 | Sattish | Mastery Blg. Contracting | 3761822 | Barsha 2nd, Dubai | 1264 | 1st, LR, TR | 3 | 1st, LR, TR | 3 | 1264 |  |  |  |  | Completed
16 | 179 | AK-24-186 | Hussein | Gulf Modern Contracting_Rashid Villa | 3435493 | Al Wasl, Dubai | 1507 | GF, 1st, Roof | 3 | GF, 1st, Roof | 3 | 1507 |  |  |  |  | Completed
17 | 183 | AK-24-173 | Raman | Modern Building Contracting_3B+G+17 - Arjan (Samana) | 6731129 | Arjan, Dubai | 51302 | B2, B1, GF, 1 - 17, R | 21 | B2, B1, GF, 1 to 17, R | 21 | 50628.17
18 | 184 | AK-24-289 |  | High Beam _ B+G+1+R PLOT 01- Al Sattari | 6317124 | HADAEQ Shk Mohd Rashid | 806 | GF, 1st, Roof, TR | 4 | GF, 1st, Roof, TR | 4 | 806 |  |  |  |  | Completed
19 | 186 | AK-24-299 | Sattish | DSCA - 1Wood Residence | 6817237 | Barsha 4th South, Dubai | 24538 | P1-P4, P4 High, 1 - 12, R | 18 | P1-P4, P4 High, 1 - 12, R | 18 | 24538 |  |  |  |  | Completed
20 | 188 | AK-24-281 | Sattish | Cairo contracting B+G+5+R | 6456413 | Wadi Al Safa 3, Dubai | 11379 | 1 - 5, TR | 6 | 1 - 5, TR | 5 | 11379 |  |  |  |  | Completed
21 | 189 | AK-24-365 | Hussein | Waleed Villa- Gulf modern Contracting | 3435504 | Al Wasl, Dubai | 951 | 1st, R | 2 | 1st, R | 2 | 951 |  |  |  |  | Completed
22 | 192 | AK-24-338 | Hussein | Aroma_G+9- Divine Hills | 5919626 | Jabal Ali First, Dubai | 29093 | 1-3, 4-9, R | 10 | 1-9, R | 10 | 29093 |  |  |  |  | Completed
23 | 193 | AK-24-132 | Sattish | Indo Gulf G+1P+10TYP | 59110351 | Jabal Ali First, 591, Dubai | 27732 | P, 1-2, 3-10, R, Rdeck | 13 | P, 1 to 10, R | 0 | 27732
24 | 194 | AK-24-366 | Sattish | Al Rakha Group -Terrazo | Terrazo Residences | Dubai, UAE | 38337 | 1-5, R | 6 | 1-5, R | 5 | 38337 |  | Completed | Nil | Submitted | Completed
25 | 198 | AK-24-363 | Dharmendran | Jasaf Bldg. Technology | 3470356 & 57 | District 1, Dubai | 936 | 1st, Roof | 2 | 1, Roof | 2 | 936 |  |  |  |  | Completed
26 | 199 | AK-24-368 | Raman | Lachlan General Contracting | 223, | Mohd Zayed City, Abu Dhabi | 1709 | 1st, R, TR | 3 | 1st, R, TR | 3 | 1709 |  |  |  |  | Completed
27 | 200 | AK-24-441 | Raman | Onix villa_Nashira sultana | Afwavil012 | Jabal Ali First - 591 | 821 | 1st + R Villa + Garagge | 2 | 1st, Roof, | 2 | 821 |  |  |  |  | Completed
28 | 201 | AK-24-439 | Raman | Uniforce_Dubai Aviation City-G+4 | RF60 | Wadi Al Safa, Aviation City Dubai | 5571 | 1st, 2-4, LR | 5 | 1st, 2-4, | 4 | 5571 |  |  |  |  | Completed
29 | 202 | AK-24-51 | Dharmendran | Walkthrough contracting | 3940873 | Al Thanyah fourth | 2433 | GF, 1st, LR | 3 | [7 empty] | Completed
30 | 204 | AK-24-450 | Sattish | Naf G+2P+6 | 6185435 | Nad Al Shiba Gardens, Dubai |  | P1, P2, 1st, 2-3, 4-6, R | 9 | P1, P2, 1st, 2-3, 4-6, R | 9 | [5 empty] | Completed
31 | 206 | AK-24-303 | Sattish | Tiger_ Al Rahmania School | M1483/G5904 | Sharjah, | 20000 | 1st, 2nd & Roof | 3 | 1st, 2nd, & Part Roof | 2 | 19500 |  |  |  |  | Completed
32 | 209 | AK-24-433 | Dharmendran | Loft Contracting_ PLOT NO.IC3-E-04 | IC3-E-04 | International City Phase 3, Dubai | 6502 | 1st, 2-5, 6, R | 7 | 1, 2, 3, 4,5,6, R | 7 | 6502 |  |  |  |  | Completed
33 | 211 | AK-24-100 | Sattish | INEX Contracting- Ain Al Maha (2 Mosques) | Plot 5 - Mo-001 (North & South) | Al Jubail Island, Abu Dhabi | 653 | Roof | 2 | N-Mosque Completed | 2 | 653 |  |  |  |  | Completed
34 | 212 | AK-24-273 | Dharmendran | Grand Signature bldg. Contracting | 6489155 | Dubai Land Residence Complex | 5046 | 1 - 3, R | 4 | 1st, 2ND, 3RD, R | 4 | 5046 |  |  |  |  | Completed
35 | 213 | AK-24-522 | Dharmendran | Bin Malek Contracting- warsan 1st | 6218417 | Warsan First, Dubai | 4647 | 1, 2-4, R, UR | 6 | 1st, 2nd, 3rd, 4th, R, UR | 6 | 4647 |  |  |  |  | Completed
36 | 214 | AK-24-527 | Dharmendran | Loft Contracting PLOT NO. E-17 | IC3-E-17, | International City, Dubai | 6517 | 1, 2-5,6, R | 7 | 1st - 6TH, R | 7 | 6517 |  |  |  |  | Completed
37 | 215 | AK-24-468 | Hussein | Pivot Engineering Contracting B+G+4P+18+R | 63110686 | Hadaeq Shk Mohd Bin Rashid | 38626 | P1-P4, 1-18, R | 23 | P1-P4, 1-5, 6-18, R | 23 | 38626 |  |  |  |  | Completed
38 | 216 | AK-24-547 | Strengthening | Sharhan Bldg Cont., Onix Conslt | [12 empty] | Completed
39 | 217 | AK-24-491 |  | City Expert - Downtown | 3450429 | Downtown Dubai | 1422 | 1st, Roof | 2 | 1st, Roof | 2 | 1422 |  |  |  |  | Completed
40 | 218 | AK-24-568 | Raman | Super World Building Contracting | 9131390 | Madinat Hind 3, Dubai | 620 | 1, Roof | 2 | 1st | 2 | 620 |  |  |  |  | Completed
41 | 221 | AK-24-524 | Dharmendran | Beam Construction 1B+G+1ST+6TYP.FR+HC | 1241205 | Al Muraqqabat, Deira, Dubai | 6822 | 1-3, 4-7, HC, Terrace | 9 | 1,2,3, 4, 5, 6, 7, HC, TR | 9 | 6822 |  |  |  |  | Completed
42 | 222 | AK-24-607 | Strengthening | Ace Metal Vision & Steel Works | [12 empty] | Completed
43 | 223 | AK-24-534 | Hussein | Delta Engineering Consultant _ Royal Pearls [JOH] - Shamandy | 6184116, 6184086 | Nad Al Shiba 1st, Dubai | 31000 |  |  |  |  | 31000 |  |  |  |  | Completed
44 | 226 | AK-24-615 |  | Al Qahera Contracting [Strengthening] Pelagos |  |  |  | Strengthening | [8 empty] | Strengthening
45 | 227 | AK-24-620 |  | Anson Construction | C33 | Yas Island, Abu Dhabi | [10 empty] | Completed
46 | 228 | AK-24-623 | Dharmendran | High Beam G+2 | 606 | Al Wasl, Dubai | 1468 | G,1, R, TR | 4 | G,1, R, TR | 4 | 1468 |  |  |  |  | Completed
47 | 228 | AK-24-623 |  | High Beam G+2 | 707 | Al Wasl, Dubai | 1391 | G,1, R, TR | 4 | G,1, R, TR | 4 | 1391 |  |  |  |  | Completed
48 | 228 | AK-24-623 |  | High Beam G+2 | 909 | Al Wasl, Dubai | 1500 | G,1, R, TR | 4 | G,1, R | 4 | 1500 |  |  |  |  | Completed
49 | 229 | AK-24-592 (187) | Sattish | 6453245 (P187) | Wadi Al Safa 3, Dubai | 7930 | GF, 1-5, R, TR | 8 | GF, 1 - 5, R | 8 | 7975.19 | - |  | All Levels | To Start | To Do | To Update
50 | 231 | AK-24-593 | Sattish | INEX Contracting - Seef Al Jubail Mosque Plot no P-94 [joh] | P-94 | Jubail Island, Abu Dhabi | 683 | LR & TR | 2 | LR & TR | 2 | 683 |  |  |  |  | Completed
51 | 232 | AK-24-599 | Dharmendran | Buildtech Construction | 1010389 DIA-RE0043 | Dubai Islands, Dubai | 9940 | P1, P2, 1 to 8, Lower Roof | 11 | P1, P2, 1, to 8, LR | 11 | 9940 |  |  |  |  | Completed
52 | 233 | AK-25-009 | Raman | Shine Square, G+4+R | RC-83 | Dubai South | 8127 | 1-4, LR, UR | 6 | 1,2,3, 4, LR, UR | 6 | 8127
| 234 | AK-24-316 | Moustafa | Costplus Contracting G+4+ROOF | RC-86 | Dubai South | 6025 | 1st, 2-4, LR | 5 | 1,2,3,4, LR | 5 | 6092 | All Done | To Update | To Update | To Update
| 239 | Ak-24-422 | Moustafa | ITEC Const 2B+G+10+R | IC1-CBDH-02 | Warsan 1621, Dubai | 18750 | 1, 2-10, R | 11 | 1, 2, 3, 4, 5, 6, 7, 8 | 8 | 13530.5 | All Done | To Update | To Update | To Update
53 | 240 | AK-25-034 | Sattish | FORDROUGH BUILDING CONTRACTING (B+G+1) | 6454334, Wadi Safa 3 | Barari, Dubai | 1515 | FF, LR | 2 | FF, LR | 2 | 1515 |  |  |  |  | Completed
54 | 241 | AK-24-652 | Raman | Aroma JVC- 1B+G+3P+8F+R | JVC 10B MRM 001, JVC | Dubai | 16846 | GF, P1,P2,P3,1 TO 8, R | 13 | GF, P1,P2,P3,1 TO 8, R | 13 | 16846 |  |  |  |  | Completed
| 242 | AK-24-375 |  | Hamec Consultant - WAHEEDA
55 | 244 | AK-24-395 | Hussein | Al Shafar G+1 Villa | 3320703 | Jumeirah 1, Dubai | 1012 | 1st, Roof | 2 | 1ST, Roof | 2 | 1012 |  |  |  |  | Completed
56 | 245 | AK-24-525 |  | Modern building Contracting B+G+1+R | 3670339 | Satwa, Umm Al Shief | 2438 | GF, 1st, RF, TR | 4 | GF, 1st, RF, TR | 4 | 2438 |  |  |  |  | Completed
| 246 | AK-24-59 | Moustafa | Al Shafar Helix Tower | 6727717 | Al Barsha South 2ND | 22993 | 1-21, Roof | 20 | 1 to 21 | 21 | 24163.43 | All Done | To Update | To Update | To Update
57 | 248 | AK-25-043 | Raman | Al Haqiqi Bldg Cont G+2 | 9140810 | Madinath Hind 4th, Dubai | 580 | 1st, 2nd Roof | 3 | 1,2, Roof | 3 | 580 |  |  |  |  | Completed
| 252 | AK-25-041 | Moustafa | Sumer Cont, B+G+9+R | 6731228 | Al Barsha South 3 | 40122 | G, 1-9, R, UR | 12 | GF, 1 to 9 | 10 | 35873.56 | UR BAL | To Update
58 | 254 | AK-24-642 | Raman | NAJ Contracting G+1 | 3435420 | Al Wasl, Dubai | 723 | 1, Lroof | 2 | 1 | 1 | 696
| 256 | AK-24-536 |  | City Experts-Burjeel Hospital- (Strengthening)
59 | 257 | AK-25-111A | Dharmendran | ASHIYANA CONTRACTING (Site#281) G+3P+12+R | JVC10XMRM001 | JVC, Dubai | 24020 | P1-P3, 1, 2-11, 12, R | 16 | P1, P2, P3,1 - 12, R | 15 | 25424.14
60 | 257 | AK-25-111B | Dharmendran | ASHIYANA CONTRACTING (Site#282) B+G+9+R | 6731245 | Al Barsha South Dubai | 24253 | GF, 1, 2, 3-9, LR, R | 12 | GF,1, to 9, LR | 11 | 23228
61 | 260 | AK-24-621 | Dharmendran | Lamida Contracting G+3P+19F+R | 3460608 | Business Bay, Dubai | 47971 | P1, P2, P3, 1-19, LR | 23 | P1, P2, P3, 1-19, LR | 23 | 47971
62 | 261 | AK-25-042 | Dharmendran | JVC14EMRP005 | JVC, Dubai | 18276 | P, 1-5, R | 7 | P,1 to 5, R | 7 | 18276 |  |  |  |  | Submitted | Completed
63 | 262 | AK-25-175 | Tendon Locking | Bin Odeh bldg Cont. | [12 empty] | Completed
64 | 263 | AK-24-627 | Raman | Classic Star Bldg Cont. B+G+1 | 63110692 | Dubai Hills | 1147 | 1, Lroof | 2 | 1st, Lroof | 2 | 1147 |  |  |  |  | Completed
65 | 264 | AK-24-493 | Sattish | Al Usr Bldg. Contracting co - G+4+60% ROOF | 395/M-21 | Mulk, Sharjah | 3705 | 1, 2-4, R, TR | 5 | 1, 2, 3, 4, R, TR | 5 | 3705 |  |  |  |  | Completed
66 | 265 | AK-25-186 |  | DECOR N MORE | [12 empty] | Completed
67 | 266 | AK-25-191 | Scanning | Mastery Blg. Contracting | [12 empty] | Completed
68 | 267 | AK-24-234 | Raman | Golden Wall Ajman G+1+R | 1367 | Zohrah Secor | 1245 | BC, GFC, R | 3 | BC, GFC, R | 3 | 1245 |  |  |  |  | Completed
69 | 268 | AK-25-097 | Dharmendran | ARAB CONTRACTS | 6453240 | Wadi Al Safa 3, Dubai | 7147 | G, 1-5, R, UR | 8 | GF, 1 to 5, R, UR | 8 | 7147 |  |  |  |  | Completed
70 | 270 | AK-25-164 | Raman | Dsca Ozone Project B+G+4P+21+R | JVC13 NOH R400B | JVC, Dubai | 24342 | Level 2 - 21, R | 20 | 2 to 21, R | 20 | 24000 |  | Done | Done | Submitted | Completed
71 | 271 | AK-24-411A | Raman | Al Rakha Avonlea 1 | DXB-228-01 | Mina Rashid, Dubai | 21500 | 1st, 2-6, 7,8, 9, R | 10 | 1,2, 3, 4, 5, 6 | 6 | 17499 |  |  |  |  | Completed
72 | 271 | AK-24-411A | Raman | Avonlea 2 |  |  | 25269 | [9 empty] | Completed
73 | 271 | AK-24-411B | Raman | Al Rakha Bayline | DXB-228-02 | Mina Rashid, Dubai | 25269 | P, 1st, 2-6, 7-8, R | 10 | P, 1st, 2-6, 7-8, R | 10 | 25269 |  |  |  |  | Completed
74 | 272 | AK-24-637 | Raman | Skada Construction G+2P+8 | DIA-RE-1179 | Dubai Islands, Dubai | 12440 | P1, P2, 1-8, Roof | 11 | GF P1, P2, 1 -8 | 10 | 11200
75 | 276 | AK-25-188 | Raman | CHC Dubai Police | 8142256 | AL ROWAIYAH 3 | 4740 | (Mezz,Roof) + (1st, 2nd & R) |  |  |  | 4740 |  | Done | Done | Submitted | Completed
76 | 277 | AK-25-461 | Sadayappa/Ravi | Villa -Smart Structure Cont. | 78 | Al Majaz 03, Abu Dhabi | 2660 | GF, 1st Roof | 3 |  | 1 | [5 empty] | Completed
77 | 278 | AK-25-285 | Raman | KTC INTERNATIONAL L.L.C | 6241285 | Warsan fourth, 624 | 8120 | P, 1 to 6, R | 8 | P, 1 to 6, R | 8 | 8120
78 | 279 | AK-25-236 | CANCELLED | RAQ + Dynamic Design Studio | 321 | Al Melaheyah, Dubai | 39696 | CANCELLED | 7 | [7 empty] | Completed
79 | 280 | AK-25-218 | Dharmendran | CHICAGO Contr + Mimar Architect | AC3-11 | Dubai South | 8719 | 1,2,3,4,5,Roof | 6 | 1,2,3, 4, 5, Roof | 6 | 8719
80 | 290 | AK-25-356 | Raman | B+G+1+R Uniforce | 6316642 | Dubai Hills, Dubai | 1353 | GF, 1st, R | 3 | GF, 1st, R | 1 | 1353 |  |  |  |  | Completed
81 | 291 | AK-24-282 | Sattish | G+2+R Jumeirah Park Al Maeraj | JPMVIL071-072 | Jumeirah Park Villa | 1227 | 1st, 2nd | 2 | 1, 2 | 2 | 1227 |  |  |  |  | Completed
| 293 | AK-25-269 | Dharmendran | Onix Plus | 3470937 |  | 463 | 1st, Roof | 2 | 1 , R | 2 | 463
82 | 294A | AK-25-077 | Sadayappa/Ravi | G+P+8+R Aroma (413) J243 | 3342413 | Satwa | 9787 | P, 1, 2-7, 8, R | 10 | P,1 to 8, R | 10 | 9787 |  |  |  |  | Completed
| 294B | AK-25-077 | Sadayappa/Ravi | G+P+8+R Aroma (417) J244 | 3342417 | Satwa | 9556 | P, 1, 2-7, 8, R | 10 | P,1 to 8,R | 10 | 9556 |  |  |  |  | Completed
83 | 294C | AK-25-077 | Sadayappa/Ravi | G+P+8+R Aroma (739) J245 | 3342739 | Satwa | 8343 | P, 1, 2-7, 8, R | 10 | P,1 to 8, R | 10 | 8343 |  |  |  |  | Completed
| 294D | AK-25-077 | Sadayappa/Ravi | G+P+8+R Aroma (740) J246 | 3342740 | Satwa | 8377 | P, 1, 2-7, 8, R | 10 | P,1 to 8, R | 10 | 8377 |  |  |  |  | Completed
| 294E | AK-25-077 | Sadayappa/Ravi | G+P+8+R Aroma (938) J247 | 3342938 | Satwa | 8271 | P, 1, 2-8, R | 10 | P,1 to 8, R | 10 | 8271 |  |  |  |  | Completed
84 | 299 | AK-25-297 | Ravi | Grand Signature | 3323734 | Pearl Jumeirah, Dubai | 369 | 1st | 1 | 1st | 1 | 369 |  |  |  |  | Completed
| 308 | AK-25-476 | scanning | Forces Bldg Contracting
| 310 | AK-25-431 | ONLY DESIGN | G+2P+10, Well Concept |  | Nakhlat Deira, Dubai | 16239 | GF, P1, P2, 1-10 | 13
85 | 312 | AK-25-552 |  | AD Police Engg, Al Nasiya | 95661 | Abu Dhabi | 319 | Auditorium Bldg | 1 | [7 empty] | Completed
86 | 316 | AK-25-279 |  | G+1+R Uniforce | 3660717 | Umm Suqueim | 231 | GF, 1st | 2 | GF, 1st | 2 | 231 |  |  |  |  | Completed
87 | 337 | AK-25-712 | Raman | G+1 TEKTON | 3435393 | Al Wasl Dubai | 1196 | 1st, R, TR | 3 | 1, R, TR | 3 | 1196 |  |  |  |  | Completed
| 353 | AK-25-946 | Strengthening | Villa 606-707 Strengthening
| 371 | AK-25-996 | Ravi/Scanning | Bond Interiors
| 375 | AK-25-532 | Sadayappa/Ravi | G+1 Villa MBC | 2161387 | Al Rashidiya | 351 | 1st, Roof | 2 | 2 | 2 | 351 | ROOF
| 377 | AK-25-1007 | Strengthening | High Beam Villa 909
88 | 379 | AK-25-295 | Dharmendran | B+G+1 Ankora Shafar Villa | 3621010 | Umm Suqueim | 1743 | GF, 1st | 2 | GF | 0.5 | 1137.33 |  |  |  |  | Completed
89 | 382 | AK-25-1022 | Raman | G+4+R Shine Square | RB-39 | Dubai South | 6375 | 1-4, Roof | 5 | 1-4, Roof | 5 | 6375 |  |  |  |  | Completed
90 | 422 | AK-26-259 | SCANNING | BATHROOM
91 | 427 | AK-26-360 | GROUTING | B+G+12 SHINE SQUARE | IC3-01.01 | WARSAN 4TH 624
92